## Budget
| Category | Wadman Estimate | WSU Estimate | Actual | GIK
General Conditions | [6 empty] | Total Expenditures by Ogden City
| Lot acquistion costs (Ogden City) | 0 | 35000 | 0 | 35000 | Donated by Ogden City | 43301.62
| Plans by WSU | 0 | 2610 | 2610 | 2610 | Sweat Equity by Jeremy's Senior Project Group | Total Expenditures with Wadman
| Engineering by Tom Hales | 0 | 1020 | 0 | 1020 | Paid by Ogden City Planning | 248269.6
| Plan Review Fee | 0 | 150 | 70.5 | 0 |  | Total Donations/ Discounts
| Building permits & Impact Fees (Ogden City) | 0 | 6500 | 0 | 7281.62 | Paid for by Ogden City Planning ($5597.56 Impact Fees, 1234.06 Inspection Fees, $450 SWPP Inspection Fee) | 123267.8
01-1000L | General Conditions (Temp Power, Porta Pottie, SWPP) | 5589 | 1500 | 1545.15 | 0 |  | Total Sweat Equity
01-1020G | Overhead | 9595 | 0 | 9595 | 20000 | Concrete Blankets, Furnace, Fuel, Warehouse deliveries Donated by Wadman, Profit | 27854
01-1170G | Contingency Allowance | 10075 | 0 | 0 | 0 |  | Total Weber Expenditures
01-118G | Insurance & Bonds | 3936 | 0 | 2069 | 0 |  | 66325.86
01-1210G | Wadman Safety | 857 | 0 | 857 | 0
01-1300L | Wadman Project Assistant | 4457 | 0 | 2000 | 0
01-1310L | Wadman Project Manager | 10286 | 0 | 9500 | 0
| Superintendent | 0 | 10000 | 0 | 10000 | Sweat Equity by Jeremy' class $500/week for 20 weeks
| Waste Removal | 0 | 1500 | 0 | 1500 | Paid for by WSU FM contract | 509018.88
02-2100G | Temp Fence | 1343 | 1500 | 1222.68
| Overhead & Profit included in change orders |  |  | -2122
| Final Cleaning | 0 | 500 | 0 | 500 | Sweat Equity by Jeremy's Senior Project Group
| HERS Rating Fee |  |  | 300
| Appraisal Fee |  |  | 500
| Temp Power |  |  | 1345.5
| Net Metering App Fee |  |  | 271.19
| Power Connection Fee |  |  | 4493
| Reimbursement to neighbor for power |  |  | 500
| Blain Anderson generator part |  |  | 414
| Water Bills |  |  | 92 |  |  |  | 250000 | Original Estimate
| Mobile Mini |  |  | 979.2 |  |  |  | 17848 | Utilities across 28th Street
| Tools |  |  | 2569.55 |  |  |  | 30000 | Finish Basement
Sub total |  | 46138 | 60280 | 38811.77 |  |  |  | 7036.16 | Unforseen Site Conditions (Curb & Gutter/ Asphalt patch)
Site Work | [7 empty] | 11100 | Powerr Connection Costs
| Survey | 0 | 0 | 1800 | 0 |  |  | 315984.16
| Title Fee |  |  | 175 |  |  |  | vs
| Soil Inspection by Engineer |  | 0 | 600 | 0 |  |  | 314595.46 | Out of Pocket Expenses
| Sewer & Water Laterals across 28th Street | 0 | 0 | 17848.22 | 0 | Did not know about this when MOU with Ogden City was signed
| Excavation, Sewer & Water Lines, remove sidewalk, approaches, curb & gutter | 15000 | 15000 | 21462.5 | 1500 | Sweat Equity by Jeremy's Senior Project Group
| Landscaping Materials | 0 | 1500 | 1924.78 | 800 | Four $200 trees donated by Ogden City Parks Department
| Landscaping Labor (Sprinklers, Curbing, Topsoil, grading) | 0 | 0 | 10756.25 | 0
| Sod | 0 | 2000 | 2320 | 1000 | Sweat Equity by FM
| Asphalt and Concrete Cuts | 0 | 0 | 175 | 0
| Elecrical Boring |  |  | 7400
| Neighbor Extortion Costs |  |  | 3700
| Perimeter Drain |  |  | 737.12
| Fence repair and extension on West Property line |  |  | 562.38
| Asphalt Patch | 0 | 0 | 2036.16 | 0 | Had to replace 18" of asphalt in front of replaced Curb and Gutter
Sub total |  | 15000 | 18500 | 71497.41
Concrete
| ICF Forms for Home | 7737 | 9000 | 8906.38 | 1865.85 | Discounted by Build Block
| ICF Labor & Water Proofing for Home | 0 | 750 | 1199.37 | 4750 | Donated by Jeremy's Senior Project Group
| Gravel Conveying & Concrete Prep | 3700 | 3500 | 3700 | 1700 | Donated by Jeremy's Senior Project Group
| Concrete Labor | 22210 | 22000 | 22210 | 0 | All Concrete lumped into one bid
| Foundation Plaster | 750 | 500 | 0 | 0 | Included with Exterior because it was stucco
| Concrete, Gravel, Road Base | 23285 | 20000 | 24372.75 | 2400 | 10% Discount by Parsons
| Rebar, Window Wells, bolts, straps | 2140 | 2000 | 2193.63 | 1200 | Donation by Boman Kemp
Sub total |  | 59822 | 57750 | 62582.13
Wood
| SIPS Exterior Walls | 7988 | 9000 | 7988 | 1012 | Discount by Big Sky R Value
| Framing Lumber & Finish Package (Inc, ext. doors) | 12500 | 12500 | 17343.88 | 0
| Framing Labor & Nails/Staples | 7806 | 9500 | 20923.67 | 1644 | Sweat Equity by Jeremy's Senior Project Group
| Trusses | 0 | 6600 | 0 | 7309.95 | Donation from Automated Trusses
| Cabinets | 8500 | 8500 | 0 | 8500 | Donated by Lewis Cabinets and Installed by Wilder Cabinets
| Countertops | 3000 | 3000 | 3000 | 500 | Discount by Valley View Granite
| Interior Trim Labor | 0 | 1500 | 1156 | 500 | Donated by Jeremy
sub total |  | 39794 | 50600 | 50411.55
Moisture Protection
| Roofing Labor & Materials | 6601 | 4500 | 6601 | 0
| Exterior (Siding) Includes labor | 16642 | 8500 | 17942 | 0
| Attic Insulation | 1280 | 1300 | 1280 | 500 | Rim Joist insulation and air sealing donated by Jeremy's Senior Project Group
Sub total |  | 24523 | 14300 | 25823
Doors & Windows
| Windows | 0 | 3000 | 0 | 4200 | $4200 Windows donated by Vitro Glass and Amsco Windows
| Windows Install | 0 | 500 | 390.52 | 500 | $500 Install Donated by Jeremy's Senior Project Group
| Garage Door | 1536 | 1500 | 1536 | 0
| Shower Glass Door | 460 | 0 | 0 | 0
Sub total |  | 1996 | 5000 | 1926.52
Electrical
| Electrical Labor & Materials | 6879 | 7000 | 10515.89 | 250 | Labor donated by D Tech electrical program
| Electrical Fixtures | 0 | 2000 | 1521.34 | 2500 | WAC Lighting Donating
| Solar Array with Battery | 0 | 22500 | 0 | 46136 | Solar Array Donated by ES Solar, Goal Zero, & Mission Solar
sub total |  | 6879 | 31500 | 12037.23
Plumbing
| Plumbing Labor | 0 | 3500 | 1887.69 | 2400 | Davis Technical College to donate the rough labor, but we had to hire the instructor to finish because of Covid
| Plumbing Material | 0 | 3000 | 6977.39 | 0
Sub total |  | 0 | 6500 | 8865.08
Mechanical
| HVAC | 13500 | 15000 | 15100 | 10000 | Donation by New City, ARS, and RMP
Sub total |  | 13500 | 15000 | 15100
Interior Finishes
| Drywall | 7852 | 6000 | 12099 | 0 | Finished the basement
| Aerobarrier | 0 | 2500 | 0 | 2450 | Donated by Mitch Spence Aerobarrier
| Painting Material |  | 2500 | 0 | 3500 | Donated by Benjamin Moore
| Painting Labor | 0 | 3500 | 3500 | 0
| Flooring Material | 0 | 5500 | 9051.26 | 0
| LVP Install | 0 | 1000 | 1596 | 0
| Mirrors & Interior Finishes | 0 | 1500 | 917.12 | 0
| Appliances | 0 | 2500 | 0 | 8644 | Beko Applianced Donating
| Window Coverings |  |  | 0 | 750 | Donated By In Pro Architectural Products
Sub total |  | 7852 | 25000 | 27163.38
Misc.
| Misc Supplies | 0 | 500 | 377.39
Sub total |  | 0 | 500 | 377.39
| SUBTOTAL | 215504 | 284930 | 314595.46 | 194423.42 | Total Value of Home | 509018.88
| Ogden Lot + Permit Fees |  |  | 43301.62
| Realtor Fee |  |  | 3500
| Subtotal including lot & sales |  |  | 361397.08
| Cost/ SF for 2450 Finished SF | 147.509
| Value/ SF | 207.7628

## SE
| Category | Wadman Estimate | WSU Estimate | Actual | GIK
General Conditions | [6 empty] | Total Expenditures by Ogden City
| Lot acquistion costs (Ogden City) | 0 | 35000 | 0 | 35000 | Donated by Ogden City | 43301.62
| Plans by WSU | 0 | 2610 | 2610 | 2610 | Sweat Equity by Jeremy's Senior Project Group | Total Expenditures with Wadman
| Engineering by Tom Hales | 0 | 1020 | 0 | 1020 | Paid by Ogden City Planning | 248269.6
| Plan Review Fee | 0 | 150 | 70.5 | 0 |  | Total Donations/ Discounts
| Building permits & Impact Fees (Ogden City) | 0 | 6500 | 0 | 7281.62 | Paid for by Ogden City Planning ($5597.56 Impact Fees, 1234.06 Inspection Fees, $450 SWPP Inspection Fee) | 108267.8
01-1000L | General Conditions (Temp Power, Porta Pottie, SWPP) | 5589 | 1500 | 1545.15 | 0 |  | Total Sweat Equity
01-1020G | Overhead | 9595 | 0 | 9595 | 5000 | Concrete Blankets, Furnace, Warehouse deliveries Donated by Wadman | 27854
01-1170G | Contingency Allowance | 10075 | 0 | 0 | 0 |  | Total Weber Expenditures
01-118G | Insurance & Bonds | 3936 | 0 | 2069 | 0 |  | 66016.24
01-1210G | Wadman Safety | 857 | 0 | 857 | 0
01-1300L | Wadman Project Assistant | 4457 | 0 | 2000 | 0
01-1310L | Wadman Project Manager | 10286 | 0 | 9500 | 0
| Superintendent | 0 | 10000 | 0 | 10000 | Sweat Equity by Jeremy' class $500/week for 20 weeks
| Waste Removal | 0 | 1500 | 0 | 1500 | Paid for by WSU FM contract | 493709.26
02-2100G | Temp Fence | 1343 | 1500 | 1222.68
| Overhead & Profit included in change orders |  |  | -2122
| Final Cleaning | 0 | 500 | 0 | 500 | Sweat Equity by Jeremy's Senior Project Group
| HERS Rating Fee |  |  | 300
| Appraisal Fee |  |  | 500
| Temp Power |  |  | 1345.5
| Net Metering App Fee |  |  | 271.19
| Power Connection Fee |  |  | 4493
| Reimbursement to neighbor for power |  |  | 250
| Blain Anderson generator part |  |  | 414
| Water Bills |  |  | 92
| Mobile Mini |  |  | 979.2
| Tools |  |  | 2569.55
Sub total |  | 46138 | 60280 | 38561.77
Site Work
| Survey | 0 | 0 | 1800 | 0
| Title Fee |  |  | 175
| Soil Inspection by Engineer |  | 0 | 600 | 0
| Sewer & Water Laterals across 28th Street | 0 | 0 | 17848.22 | 0 | Did not know about this when MOU with Ogden City was signed
| Excavation, Sewer & Water Lines, remove sidewalk, approaches, curb & gutter | 15000 | 15000 | 21462.5 | 1500 | Sweat Equity by Jeremy's Senior Project Group
| Landscaping Materials | 0 | 1500 | 1924.78 | 800 | Four $200 trees donated by Ogden City Parks Department
| Landscaping Labor (Sprinklers, Curbing, Topsoil, grading) | 0 | 0 | 10756.25 | 0
| Sod | 0 | 2000 | 2320 | 1000 | Sweat Equity by FM
| Asphalt and Concrete Cuts | 0 | 0 | 175 | 0
| Elecrical Boring |  |  | 7400
| Neighbor Extortion Costs |  |  | 3700
| Perimeter Drain |  |  | 737.12
| Fence repair and extension on West Property line |  |  | 502.76
| Asphalt Patch | 0 | 0 | 2036.16 | 0 | Had to replace 18" of asphalt in front of replaced Curb and Gutter
Sub total |  | 15000 | 18500 | 71437.79
Concrete
| ICF Forms for Home | 7737 | 9000 | 8906.38 | 1865.85 | Discounted by Build Block
| ICF Labor & Water Proofing for Home | 0 | 750 | 1199.37 | 4750 | Donated by Jeremy's Senior Project Group
| Gravel Conveying & Concrete Prep | 3700 | 3500 | 3700 | 1700 | Donated by Jeremy's Senior Project Group
| Concrete Labor | 22210 | 22000 | 22210 | 0 | All Concrete lumped into one bid
| Foundation Plaster | 750 | 500 | 0 | 0 | Included with Exterior because it was stucco
| Concrete, Gravel, Road Base | 23285 | 20000 | 24372.75 | 2400 | 10% Discount by Parsons
| Rebar, Window Wells, bolts, straps | 2140 | 2000 | 2193.63 | 1200 | Donation by Boman Kemp
Sub total |  | 59822 | 57750 | 62582.13
Wood
| SIPS Exterior Walls | 7988 | 9000 | 7988 | 1012 | Discount by Big Sky R Value
| Framing Lumber & Finish Package (Inc, ext. doors) | 12500 | 12500 | 17343.88 | 0
| Framing Labor & Nails/Staples | 7806 | 9500 | 20923.67 | 1644 | Sweat Equity by Jeremy's Senior Project Group
| Trusses | 0 | 6600 | 0 | 7309.95 | Donation from Automated Trusses
| Cabinets | 8500 | 8500 | 0 | 8500 | Donated by Lewis Cabinets and Installed by Wilder Cabinets
| Countertops | 3000 | 3000 | 3000 | 500 | Discount by Valley View Granite
| Interior Trim Labor | 0 | 1500 | 1156 | 500 | Donated by Jeremy
sub total |  | 39794 | 50600 | 50411.55
Moisture Protection
| Roofing Labor & Materials | 6601 | 4500 | 6601 | 0
| Exterior (Siding) Includes labor | 16642 | 8500 | 17942 | 0
| Attic Insulation | 1280 | 1300 | 1280 | 500 | Rim Joist insulation and air sealing donated by Jeremy's Senior Project Group
Sub total |  | 24523 | 14300 | 25823
Doors & Windows
| Windows | 0 | 3000 | 0 | 4200 | $4200 Windows donated by Vitro Glass and Amsco Windows
| Windows Install | 0 | 500 | 390.52 | 500 | $500 Install Donated by Jeremy's Senior Project Group
| Garage Door | 1536 | 1500 | 1536 | 0
| Shower Glass Door | 460 | 0 | 0 | 0
Sub total |  | 1996 | 5000 | 1926.52
Electrical
| Electrical Labor & Materials | 6879 | 7000 | 10515.89 | 250 | Labor donated by D Tech electrical program
| Electrical Fixtures | 0 | 2000 | 1521.34 | 2500 | WAC Lighting Donating
| Solar Array with Battery | 0 | 22500 | 0 | 46136 | Solar Array Donated by ES Solar, Goal Zero, & Mission Solar
sub total |  | 6879 | 31500 | 12037.23
Plumbing
| Plumbing Labor | 0 | 3500 | 1887.69 | 2400 | Davis Technical College to donate the rough labor, but we had to hire the instructor to finish because of Covid
| Plumbing Material | 0 | 3000 | 6977.39 | 0
Sub total |  | 0 | 6500 | 8865.08
Mechanical
| HVAC | 13500 | 15000 | 15100 | 10000 | Donation by New City, ARS, and RMP
Sub total |  | 13500 | 15000 | 15100
Interior Finishes
| Drywall | 7852 | 6000 | 12099 | 0 | Finished the basement
| Aerobarrier | 0 | 2500 | 0 | 2450 | Donated by Mitch Spence Aerobarrier
| Painting Material |  | 2500 | 0 | 3500 | Donated by Benjamin Moore
| Painting Labor | 0 | 3500 | 3500 | 0
| Flooring Material | 0 | 5500 | 9051.26 | 0
| LVP Install | 0 | 1000 | 1596 | 0
| Mirrors & Interior Finishes | 0 | 1500 | 917.12 | 0
| Appliances | 0 | 2500 | 0 | 8644 | Beko Applianced Donating
| Window Coverings |  |  | 0 | 750 | Donated By In Pro Architectural Products
Sub total |  | 7852 | 25000 | 27163.38
Misc.
| Misc Supplies | 0 | 500 | 377.39
Sub total |  | 0 | 500 | 377.39
| SUBTOTAL | 215504 | 284930 | 314285.84 | 179423.42 | Total Value of Home | 493709.26
| Ogden Lot + Permit Fees |  |  | 43301.62
| Realtor Fee |  |  | 3500
361087.46
| Cost/ SF for 2450 Finished SF | 147.3826
| Value/ SF | 201.514
| Estimated Total Worth |  |  |  | 27854

## GIK
| Category | Wadman Estimate | WSU Estimate | Actual | GIK
General Conditions | [6 empty] | Total Expenditures by Ogden City
| Lot acquistion costs (Ogden City) | 0 | 35000 | 0 | 35000 | Donated by Ogden City | 43301.62
| Plans by WSU | 0 | 2610 | 2610 | 2610 | Sweat Equity by Jeremy's Senior Project Group | Total Donations/ Discounts
| Engineering by Tom Hales | 0 | 1020 | 0 | 1020 | Paid by Ogden City Planning | 108267.8
| Building permits & Impact Fees (Ogden City) | 0 | 6500 | 0 | 7281.62 | Paid for by Ogden City Planning ($5597.56 Impact Fees, 1234.06 Inspection Fees, $450 SWPP Inspection Fee) | Total Sweat Equity
01-1020G | Overhead | 9595 | 0 | 9595 | 5000 | Concrete Blankets, Furnace, Warehouse deliveries Donated by Wadman | 27854
| Superintendent | 0 | 10000 | 0 | 10000 | Sweat Equity by Jeremy' class $500/week for 20 weeks
| Waste Removal | 0 | 1500 | 0 | 1500 | Paid for by WSU FM contract
| Final Cleaning | 0 | 500 | 0 | 500 | Sweat Equity by Jeremy's Senior Project Group
| Excavation, Sewer & Water Lines, remove sidewalk, approaches, curb & gutter | 15000 | 15000 | 21462.5 | 1500 | Sweat Equity by Jeremy's Senior Project Group
| Landscaping Materials | 0 | 1500 | 1924.78 | 800 | Four $200 trees donated by Ogden City Parks Department
| Sod | 0 | 2000 | 2320 | 1000 | Sweat Equity by FM
Concrete
| ICF Forms for Home | 7737 | 9000 | 8906.38 | 1865.85 | Discounted by Build Block
| ICF Labor & Water Proofing for Home | 0 | 750 | 1199.37 | 4750 | Donated by Jeremy's Senior Project Group
| Gravel Conveying & Concrete Prep | 3700 | 3500 | 3700 | 1700 | Donated by Jeremy's Senior Project Group
| Concrete, Gravel, Road Base | 23285 | 20000 | 24372.75 | 2400 | 10% Discount by Parsons
| Rebar, Window Wells, bolts, straps | 2140 | 2000 | 2193.63 | 1200 | Donation by Boman Kemp
Wood
| SIPS Exterior Walls | 7988 | 9000 | 7988 | 1012 | Discount by Big Sky R Value
| Framing Labor & Nails/Staples | 7806 | 9500 | 20923.67 | 1644 | Sweat Equity by Jeremy's Senior Project Group
| Trusses | 0 | 6600 | 0 | 7309.95 | Donation from Automated Trusses
| Cabinets | 8500 | 8500 | 0 | 8500 | Donated by Lewis Cabinets and Installed by Wilder Cabinets
| Countertops | 3000 | 3000 | 3000 | 500 | Discount by Valley View Granite
| Interior Trim Labor | 0 | 1500 | 1156 | 500 | Donated by Jeremy
Moisture Protection
| Attic Insulation | 1280 | 1300 | 1280 | 500 | Rim Joist insulation and air sealing donated by Jeremy's Senior Project Group
Doors & Windows
| Windows | 0 | 3000 | 0 | 4200 | $4200 Windows donated by Vitro Glass and Amsco Windows
| Windows Install | 0 | 500 | 390.52 | 500 | $500 Install Donated by Jeremy's Senior Project Group
Electrical
| Electrical Labor & Materials | 6879 | 7000 | 10515.89 | 250 | Labor donated by D Tech electrical program
| Electrical Fixtures | 0 | 2000 | 1521.34 | 2500 | WAC Lighting Donating
| Solar Array with Battery | 0 | 22500 | 0 | 46136 | Solar Array Donated by ES Solar, Goal Zero, & Mission Solar
Plumbing
| Plumbing Labor | 0 | 3500 | 1887.69 | 2400 | Davis Technical College to donate the rough labor, but we had to hire the instructor to finish because of Covid
Mechanical
| HVAC | 13500 | 15000 | 15100 | 10000 | Donation by New City, ARS, and RMP
Interior Finishes
| Aerobarrier | 0 | 2500 | 0 | 2450 | Donated by Mitch Spence Aerobarrier
| Painting Material |  | 2500 | 0 | 3500 | Donated by Benjamin Moore
| Appliances | 0 | 2500 | 0 | 8644 | Beko Applianced Donating
| Window Coverings |  |  | 0 | 750 | Donated By In Pro Architectural Products
Sub total |  | 0 | 7500 | 0
Misc.
| Misc Supplies | 0 | 500 | 377.39
Sub total |  | 0 | 500 | 377.39
| SUBTOTAL | #REF! | #REF! | #REF! | 179423.42
| Ogden Lot + Permit Fees |  |  | 43301.62
| Realtor Fee |  |  | 3500
#REF!
| Cost/ SF for 2450 Finished SF | #REF!
| Value/ SF | #REF!

## Over Under
| Category | Wadman Estimate | WSU Estimate | Actual | GIK |  |  | Variance
General Conditions | [6 empty] | Total Expenditures by Ogden City
| Lot acquisition costs (Ogden City) | 0 | 35000 | 0 | 35000 | Donated by Ogden City | 43301.62 | 35000
| Plans by WSU | 0 | 2610 | 2610 | 2610 | Sweat Equity by Jeremy's Senior Project Group | Total Expenditures with Wadman | 0
| Engineering by Tom Hales | 0 | 1020 | 0 | 1020 | Paid by Ogden City Planning | 248269.6 | 1020
| Plan Review Fee | 0 | 150 | 70.5 | 0 |  | Total Donations/ Discounts | 79.5
| Building permits & Impact Fees (Ogden City) | 0 | 6500 | 0 | 7281.62 | Paid for by Ogden City Planning ($5597.56 Impact Fees, 1234.06 Inspection Fees, $450 SWPP Inspection Fee) | 108267.8 | 6500
01-1000L | General Conditions (Temp Power, Porta Pottie, SWPP) | 5589 | 1500 | 1545.15 | 0 |  | Total Sweat Equity | -45.15
01-1020G | Overhead | 9595 | 0 | 9595 | 5000 | Concrete Blankets, Furnace, Warehouse deliveries Donated by Wadman | 27854 | -9595
01-1170G | Contingency Allowance | 10075 | 0 | 0 | 0 |  | Total Weber Expenditures | 0
01-118G | Insurance & Bonds | 3936 | 0 | 2069 | 0 |  | 66016.24 | -2069
01-1210G | Wadman Safety | 857 | 0 | 857 | 0 |  |  | -857
01-1300L | Wadman Project Assistant | 4457 | 0 | 2000 | 0 |  |  | -2000
01-1310L | Wadman Project Manager | 10286 | 0 | 9500 | 0 |  |  | -9500
| Superintendent | 0 | 10000 | 0 | 10000 | Sweat Equity by Jeremy' class $500/week for 20 weeks |  | 10000
| Waste Removal | 0 | 1500 | 0 | 1500 | Paid for by WSU FM contract | 493709.26 | 1500
02-2100G | Temp Fence | 1343 | 1500 | 1222.68 |  |  |  | 277.32
| Overhead & Profit included in change orders |  |  | -2122 |  |  |  | 2122
| Final Cleaning | 0 | 500 | 0 | 500 | Sweat Equity by Jeremy's Senior Project Group |  | 500
| HERS Rating Fee |  |  | 300 |  |  |  | -300
| Appraisal Fee |  |  | 500 |  |  |  | -500
| Temp Power |  |  | 1345.5 |  |  |  | -1345.5
| Net Metering App Fee |  |  | 271.19 |  |  |  | -271.19
| Power Connection Fee |  |  | 4493 |  |  |  | -4493
| Reimbursement to neighbor for power |  |  | 250 |  |  |  | -250
| Blain Anderson generator part |  |  | 414 |  |  |  | -414
| Water Bills |  |  | 92 |  |  |  | -92
| Mobile Mini |  |  | 979.2 |  |  |  | -979.2
| Tools |  |  | 2569.55 |  |  |  | -2569.55
Sub total |  | 46138 | 60280 | 38561.77
Site Work
| Survey | 0 | 0 | 1800 | 0 |  |  | -1800
| Title Fee |  |  | 175 |  |  |  | -175
| Soil Inspection by Engineer |  | 0 | 600 | 0 |  |  | -600
| Sewer & Water Laterals across 28th Street | 0 | 0 | 17848.22 | 0 | Did not know about this when MOU with Ogden City was signed |  | -17848.22
| Excavation, Sewer & Water Lines, remove sidewalk, approaches, curb & gutter | 15000 | 15000 | 21462.5 | 1500 | Sweat Equity by Jeremy's Senior Project Group |  | -6462.5
| Landscaping Materials | 0 | 1500 | 1924.78 | 800 | Four $200 trees donated by Ogden City Parks Department |  | -424.78
| Landscaping Labor (Sprinklers, Curbing, Topsoil, grading) | 0 | 0 | 10756.25 | 0 |  |  | -10756.25
| Sod | 0 | 2000 | 2320 | 1000 | Sweat Equity by FM |  | -320
| Asphalt and Concrete Cuts | 0 | 0 | 175 | 0 |  |  | -175
| Electrical Boring |  |  | 7400 |  |  |  | -7400
| Neighbor Extortion Costs |  |  | 3700 |  |  |  | -3700
| Perimeter Drain |  |  | 737.12 |  |  |  | -737.12
| Fence repair and extension on West Property line |  |  | 502.76 |  |  |  | -502.76
| Asphalt Patch | 0 | 0 | 2036.16 | 0 | Had to replace 18" of asphalt in front of replaced Curb and Gutter |  | -2036.16
Sub total |  | 15000 | 18500 | 71437.79
Concrete
| ICF Forms for Home | 7737 | 9000 | 8906.38 | 1865.85 | Discounted by Build Block |  | 93.62
| ICF Labor & Water Proofing for Home | 0 | 750 | 1199.37 | 4750 | Donated by Jeremy's Senior Project Group |  | -449.37
| Gravel Conveying & Concrete Prep | 3700 | 3500 | 3700 | 1700 | Donated by Jeremy's Senior Project Group |  | -200
| Concrete Labor | 22210 | 22000 | 22210 | 0 | All Concrete lumped into one bid |  | -210
| Foundation Plaster | 750 | 500 | 0 | 0 | Included with Exterior because it was stucco |  | 500
| Concrete, Gravel, Road Base | 23285 | 20000 | 24372.75 | 2400 | 10% Discount by Parsons |  | -4372.75
| Rebar, Window Wells, bolts, straps | 2140 | 2000 | 2193.63 | 1200 | Donation by Boman Kemp |  | -193.63
Sub total |  | 59822 | 57750 | 62582.13
Wood
| SIPS Exterior Walls | 7988 | 9000 | 7988 | 1012 | Discount by Big Sky R Value |  | 1012
| Framing Lumber & Finish Package (Inc, ext. doors) | 12500 | 12500 | 17343.88 | 0 |  |  | -4843.88
| Framing Labor & Nails/Staples | 7806 | 9500 | 20923.67 | 1644 | Sweat Equity by Jeremy's Senior Project Group |  | -11423.67
| Trusses | 0 | 6600 | 0 | 7309.95 | Donation from Automated Trusses |  | 6600
| Cabinets | 8500 | 8500 | 0 | 8500 | Donated by Lewis Cabinets and Installed by Wilder Cabinets |  | 8500
| Countertops | 3000 | 3000 | 3000 | 500 | Discount by Valley View Granite |  | 0
| Interior Trim Labor | 0 | 1500 | 1156 | 500 | Donated by Jeremy |  | 344
sub total |  | 39794 | 50600 | 50411.55
Moisture Protection
| Roofing Labor & Materials | 6601 | 4500 | 6601 | 0 |  |  | -2101
| Exterior (Siding) Includes labor | 16642 | 8500 | 17942 | 0 |  |  | -9442
| Attic Insulation | 1280 | 1300 | 1280 | 500 | Rim Joist insulation and air sealing donated by Jeremy's Senior Project Group |  | 20
Sub total |  | 24523 | 14300 | 25823
Doors & Windows
| Windows | 0 | 3000 | 0 | 4200 | $4200 Windows donated by Vitro Glass and Amsco Windows |  | 3000
| Windows Install | 0 | 500 | 390.52 | 500 | $500 Install Donated by Jeremy's Senior Project Group |  | 109.48
| Garage Door | 1536 | 1500 | 1536 | 0 |  |  | -36
| Shower Glass Door | 460 | 0 | 0 | 0 |  |  | 0
Sub total |  | 1996 | 5000 | 1926.52
Electrical
| Electrical Labor & Materials | 6879 | 7000 | 10515.89 | 250 | Labor donated by D Tech electrical program |  | -3515.89
| Electrical Fixtures | 0 | 2000 | 1521.34 | 2500 | WAC Lighting Donating |  | 478.66
| Solar Array with Battery | 0 | 22500 | 0 | 46136 | Solar Array Donated by ES Solar, Goal Zero, & Mission Solar |  | 22500
sub total |  | 6879 | 31500 | 12037.23
Plumbing
| Plumbing Labor | 0 | 3500 | 1887.69 | 2400 | Davis Technical College to donate the rough labor, but we had to hire the instructor to finish because of Covid |  | 1612.31
| Plumbing Material | 0 | 3000 | 6977.39 | 0 |  |  | -3977.39
Sub total |  | 0 | 6500 | 8865.08
Mechanical
| HVAC | 13500 | 15000 | 15100 | 10000 | Donation by New City, ARS, and RMP |  | -100
Sub total |  | 13500 | 15000 | 15100
Interior Finishes
| Drywall | 7852 | 6000 | 12099 | 0 | Finished the basement |  | -6099
| Aerobarrier | 0 | 2500 | 0 | 2450 | Donated by Mitch Spence Aerobarrier |  | 2500
| Painting Material |  | 2500 | 0 | 3500 | Donated by Benjamin Moore |  | 2500
| Painting Labor | 0 | 3500 | 3500 | 0 |  |  | 0
| Flooring Material | 0 | 5500 | 9051.26 | 0 |  |  | -3551.26
| LVP Install | 0 | 1000 | 1596 | 0 |  |  | -596
| Mirrors & Interior Finishes | 0 | 1500 | 917.12 | 0 |  |  | 582.88
| Appliances | 0 | 2500 | 0 | 8644 | Beko Appliances Donating |  | 2500
| Window Coverings |  |  | 0 | 750 | Donated By In Pro Architectural Products |  | 0
Sub total |  | 7852 | 25000 | 27163.38
Misc.
| Misc Supplies | 0 | 500 | 377.39 |  |  |  | 122.61
Sub total |  | 0 | 500 | 377.39
| SUBTOTAL | 215504 | 284930 | 314285.84 | 179423.42 | Total Value of Home | 493709.26 | -29355.84
| Ogden Lot + Permit Fees |  |  | 43301.62
| Realtor Fee |  |  | 3500
361087.46
| Cost/ SF for 2450 Finished SF | 147.3826
| Value/ SF | 201.514